## Worksheet
Startup Weekly Planner - Summary View
Week of | Key Objective | Tasks Completed | Tasks Pending | Status (Overall) | Budget Used ($)
2024-04-01 | Finalize MVP Scope & Core Features | 3/5 | 2/5 | High Risk | $8,900
2024-04-08 | Recruit Core Development Team | 4/6 | 1/6 | On Track | $15,300
2024-04-15 | Design UI/UX Prototype & User Flow | 5/5 | 0/5 | Completed | $7,600
2024-04-22 | Conduct First Round of User Testing | 3/5 | 1/5 | On Track | $6,100
2024-04-29 | Begin Development Sprint #1 (Frontend) | 2/8 | 6/8 | High Risk | $18,500
2024-05-06 | Secure Seed Funding Pitch Preparation | 4/7 | 3/7 | On Track | $9,800
2024-05-13 | Launch MVP Beta (Internal Testing) | 1/3 | 2/3 | High Risk | $5,200
Total (8 Weeks) |  | 22/34 | 14/34 | On Track | $71,400