## Worksheet
Strategy Planning - Manager View
STRATEGIC OBJECTIVES & INITIATIVES
Objective ID | Strategic Objective | Initiative / Project | Owner (Manager) | Start Date | Target End Date | Status (Progress %) | Budget Allocated ($) | Risk Level
SO-001 | Increase Market Share by 15% in Q3 | New Customer Acquisition Campaign | Jane Smith | 2024-06-01 | 2024-09-30 | 85% | $175,000 | High
SO-002 | Launch 3 New Product Lines by EOY | New Product Development Phase 1 | Mark Johnson | 2024-05-15 | 2024-10-31 | 68% | $350,000 | Medium
SO-003 | Improve Customer Retention Rate by 25% | Loyalty Program Enhancement | Sarah Williams | 2024-07-10 | 2024-11-30 | 55% | $95,000 | Low
SO-004 | Optimize Operational Efficiency by 20% | Process Automation Initiative | Daniel Kim | 2024-06-25 | 2025-03-15 | 34% | $410,000 | High
SO-005 | Expand into Southeast Asia Market by 2025 | Multinational Entry Strategy Development | Lisa Tran | 2024-08-15 | 2025-11-30 | 18% | $75,000 | Medium
Key Performance Indicators (KPIs) Overview
Overall Progress: | 64%
On Track (≥ 70%): | 2 / 5 Initiatives
At Risk (40%-69%): | 2 / 5 Initiatives
Delayed (< 40%): | 1 / 5 Initiatives