## Worksheet
STRATEGY PLANNING - PLANNING VIEW
Quarter | Objective | KPI Target | Current Status | Milestone Date | Owner | Risk Level | Action Items / Notes
Q1 2024 | Increase Market Share by 5% | Market share: 23% | In Progress | March 31, 2024 | Marketing Team | Moderate | Digital campaign launch scheduled.
Q1 2024 | Launch New Product Line | 3,000 units sold by end of Q1 | On Track | April 15, 2024 | R&D & Sales Team | Low | Fulfillment partnership finalized.
Q2 2024 | Improve Customer Retention Rate to 85% | CRR: 85% | Needs Attention | June 30, 2024 | Customer Success Team | High | Survey data indicates need for improved onboarding.
Q2 2024 | Leverage Data Analytics for Decision Making | Deploy 3 new dashboards by Q2 end | In Progress | May 31, 2024 | Data Analytics Team | Low | Demo completed; feedback collected.
SUMMARY METRICS (Q1 - Q2 2024)
Total Objectives |  |  | 5 | On Track:75% |  |  | On Schedule:70%
NEXT STEPS & DEPENDENCIES
- Finalize Q3 2024 KPIs by May 15 - Secure budget approval for digital transformation initiative - Conduct quarterly strategy review meeting on June 5