## Worksheet
Strategy Planning - Chore Chart (Business Use)
Task / Responsibility | Owner | Deadline | Status | Progress (% Done)
Develop Quarterly Strategy Roadmap | Executive Team | 2023-10-15 | In Progress | 65%
Market Research & Competitor Analysis | Marketing Department | 2023-10-10 | Completed | 100%
Resource Allocation Plan | Finance & Operations | 2023-10-18 | Pending | 0%
Departmental Goal Alignment Session | HR & Department Heads | 2023-10-12 | Completed | 100%
Identify Key Performance Indicators (KPIs) | Strategy Team | 2023-10-14 | In Progress | 75%
Leadership Approval & Sign-off | CEO & Board of Directors | 2023-10-20 | Pending | 0%
Communicate Strategy to All Staff | Internal Communications | 2023-10-25 | Pending | 0%
Milestone Review Meeting (Mid-quarter) | Project Management Office | 2023-11-05 | Pending | 0%
Evaluate Strategy Execution & Adjustments | Strategy Team & Leadership | 2023-11-30 | Pending | 0%
Final Strategy Report & Presentation | Executive Team | 2023-12-15 | Pending | 0%
Overall Project Status: |  |  |  | 68% Complete