## Worksheet
Advanced Gantt Chart – Strategy Planning
Task / Milestone | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Market Research & Analysis | 2024-04-05 | 2024-05-15 | 41 | In Progress
Competitive Analysis | 2024-04-05 | 2024-05-15 | 41 | In Progress
Customer Needs Assessment | 2024-04-15 | 2024-05-10 | 26 | In Progress
Market Research Completed | 2024-05-15 | 2024-05-15 | 0 | Milestone Achieved
Phase 2: Strategic Framework Design | 2024-05-16 | 2024-07-31 | 77 | In Progress
SWOT Analysis | 2024-05-16 | 2024-06-15 | 31 | In Progress
Objective & KPI Definition | 2024-06-16 | 2024-07-31 | 46 | In Progress
Strategy Draft Approved | 2024-07-31 | 2024-07-31 | 0 | Milestone Achieved
Phase 3: Action Plan & Resource Allocation | 2024-08-01 | 2024-10-15 | 76 | In Progress
Project Timeline & Dependencies | 2024-08-01 | 2024-09-15 | 46 | In Progress
Team Assignment & Budgeting | 2024-09-16 | 2024-10-15 | 31 | In Progress
Implementation Plan Finalized | 2024-10-15 | 2024-10-15 | 0 | Milestone Achieved
Phase 4: Strategy Execution | 2024-10-16 | 2025-03-31 | 168 | Pending Start
Quarterly Review & Adjustments | 2024-11-30 | 2025-03-31 | 153 | Pending Start
Critical Path: Final Review & Reporting | 2025-03-15 | 2025-03-31 | 17 | Pending Start
© 2024 Advanced Strategy Planning Gantt Chart ¦ This template is designed for strategic project tracking in Excel-like format.