## Worksheet
Strategy Planning - Gantt Chart (Analysis View)
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status
T1 | Analyze Market Trends | 2024-04-01 | 2024-04-15 | 15
T2 | Competitor Benchmarking | 2024-04-10 | 2024-05-10 | 30
T3 | SWOT Analysis | 2024-05-01 | 2024-05-15 | 15
T4 | Define Strategic Objectives | 2024-05-16 | 2024-05-31 | 16
T5 | Resource Allocation Planning | 2024-06-01 | 2024-06-15 | 15
T6 | Finalize Strategy Document | 2024-06-16 | 2024-07-01 | 15
M1 | Strategy Approval | 2024-07-05 | 2024-07-05 | - | Milestone