## Worksheet
Strategy Planning - Gantt Chart (Client View)
Project Timeline & Progress Overview
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status | Progress (%)
T001 | Market Research & Analysis | 2025-04-01 | 2025-04-15 | 15 | In Progress
T002 | Competitor Benchmarking | 2025-04-16 | 2025-04-30 | 15 | In Progress
T003 | Customer Segmentation | 2025-05-01 | 2025-05-14 | 14 | In Progress
T004 | SWOT Analysis | 2025-05-15 | 2025-05-31 | 17 | Delayed
T005 | Strategic Goals Definition | 2025-06-01 | 2025-06-14 | 14 | Completed
T006 | Key Performance Indicators (KPIs) | 2025-06-15 | 2025-06-30 | 16 | In Progress
T007 | Final Strategy Presentation | 2025-07-01 | 2025-07-15 | 15 | In Progress
Total Duration: 130 days