## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress
Initiate Strategy Framework | 2024-03-01 | 2024-03-15 | 15 | In Progress
Market Analysis & Research | 2024-03-16 | 2024-04-15 | 31 | In Progress
Competitor Benchmarking | 2024-04-16 | 2024-05-15 | 30 | In Progress
Define Objectives & KPIs | 2024-05-16 | 2024-05-31 | 16 | In Progress
Develop Action Plans | 2024-06-01 | 2024-07-31 | 61 | In Progress
Resource Allocation & Budgeting | 2024-08-01 | 2024-08-31 | 31 | In Progress
Finalize Strategy Document | 2024-09-01 | 2024-09-30 | 30 | Delayed
Executive Approval & Presentation | 2024-10-01 | 2024-10-31 | 31 | Completed
Total Duration | 273 Days |  | 273 | Avg Progress