## Worksheet
Strategy Planning - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
R01 | Market Research Phase I | 2023-10-01 | 2023-11-15 | In Progress
R02 | Competitor Analysis | 2023-10-15 | 2023-11-30 | In Progress
S01 | Core Strategy Development | 2023-12-01 | 2024-01-31 | Not Started
M01 | Strategy Approval (Milestone) | 2024-01-31 | 2024-01-31 | Milestone Achieved
I01 | Implementation Roadmap | 2024-02-01 | 2024-03-31 | Not Started
E01 | Phase I Execution (Q2 2024) | 2024-04-01 | 2024-06-30 | Not Started
O01 | Performance Review & Optimization | 2024-07-01 | 2024-09-30 | Not Started
Updated on: October 2023 ¦ Data Version ¦ Strategy Planning Gantt Chart