## Worksheet
Large Business Strategy Planning Gantt Chart
Task / Milestone | Start Date | End Date | Duration (Days) | Progress
Q1 2024 - Strategic Assessment & Market Research
Market Analysis & Competitive Benchmarking | Jan 1, 2024 | Feb 15, 2024 | 46
SWOT Analysis & Strategic Positioning | Jan 10, 2024 | Feb 28, 2024 | 50
Strategic Framework Approval | Feb 28, 2024 | Feb 28, 2024 | 1
Q2 2024 - Goal Setting & Initiative Planning
Define Long-Term Objectives (3-5 Year) | Mar 1, 2024 | Apr 15, 2024 | 46
Initiative Roadmap Development | Mar 10, 2024 | May 10, 2024 | 61
Annual Strategy Plan Finalization | May 15, 2024 | May 15, 2024 | 1
Q3 2024 - Resource Allocation & Implementation
Resource Budgeting & Team Assignment | Jun 1, 2024 | Jul 15, 2024 | 45
Technology & Infrastructure Upgrade | Jul 1, 2024 | Aug 31, 2024 | 62
Implementation Kickoff Meeting | Sep 1, 2024 | Sep 1, 2024 | 1
Q4 2024 - Monitoring & Review
Quarterly Performance Tracking | Oct 1, 2024 | Dec 31, 2024 | 91
Annual Strategy Review & Adjustment | Nov 1, 2024 | Dec 15, 2024 | 45
2024 Strategy Annual Report Submission | Dec 31, 2024 | Dec 31, 2024 | 1