## Worksheet
Strategy Planning - Gantt Chart (Manager View)
Task | Start Date | End Date | Duration (days) | Progress | Responsible Team
Market Research & Analysis | 2023-10-01 | 2023-10-15 | 15 |  | Marketing Team
Competitor Benchmarking | 2023-10-10 | 2023-10-25 | 16 |  | Strategy Team
MVP Development | 2023-10-20 | 2023-11-30 | 41 |  | Engineering Team
User Testing Phase I | 2023-11-15 | 2023-11-30 | 16 |  | Product Team
Final Product Refinement | 2023-12-01 | 2023-12-15 | 15 |  | Engineering & Design
Launch Preparation Phase
Marketing Campaign Planning | 2023-12-10 | 2023-12-31 | 22 |  | Marketing Team
Launch Event Preparation | 2023-12-15 | 2024-01-05 | 21 |  | Operations Team
Final Delivery & Launch |  |  |  |  | Executive Team
Updated as of October 5, 2023 ¦ Manager View - Strategy Planning Gantt Chart