## Worksheet
Task/Activity | Start Date | End Date | Milestones & Dependencies
|  |  | Phase I | Phase II | Phase III | Status | Owner | % Complete (Progress)
Project Initiation & Scope Definition | 2024-04-01 | 2024-04-15 | ✔️ |  |  | In Progress | Project Manager | 65%
Market & Competitor Analysis | 2024-04-16 | 2024-05-15 |  | ✔️ |  | In Progress | Market Analyst | 55%
SWOT & Risk Assessment | 2024-05-16 | 2024-06-15 |  |  | Pending | Lead Strategist | 20%
Strategic Objective Setting | 2024-06-16 | 2024-07-15 | Pending | Pending |  | Strategic Director | 5%
Task/Activity | Start Date | End Date | Milestones & Dependencies
|  |  | Phase I | Phase II | Phase III | Status | Owner | % Complete (Progress)
Resource Allocation & Budgeting | 2024-07-16 | 2024-08-15 | Pending | Pending |  | Finance Lead | 8%
Stakeholder Alignment Workshop | 2024-08-16 | 2024-09-15 | Pending | Pending |  | Project Manager | 5%
Final Strategy Document Draft | 2024-09-16 | 2024-10-31 | Pending | Pending |  | Strategy Lead | 2%
Final Review & Approval | 2024-11-01 | 2024-11-30 | Pending | Pending |  | Executive Committee | 0%
Task/Activity | Start Date | End Date | Dependencies & Notes
|  |  | Previous Task Dep. | Next Task Dep. | Status Summary | Comments / Risks
Phase I - Research & Analysis | 2024-04-01 | 2024-06-15 | None | SWOT Assessment, Objective Setting | In Progress (65%) | Depends on stakeholder availability; moderate risk in timeline.
Phase II - Planning & Framework | 2024-06-16 | 2024-10-31 | Market Analysis, SWOT Report | Strategy Draft, Final Approval | Pending (28% avg) | Resource constraints may impact timeline. Monitor closely.
Phase III - Finalization & Execution Readiness | 2024-11-01 | 2024-11-30 | Final Draft Review | N/A (End of Project) | Pending (5% avg) | Approval required by leadership team. Critical path.
Overall Project Status Summary |  |  |  | 65% Complete (Est.) | Target completion by Nov 30, 2024. No major delays detected.