## Worksheet
Strategy Planning Gantt Chart - Office Use
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
1 | Phase 1: Initial Assessment | 2024-04-01 | 2024-04-15 | 15 | In Progress
1.1 | Market Research & Analysis | 2024-04-01 | 2024-04-07 | 7 | In Progress
1.2 | SWOT Analysis | 2024-04-08 | 2024-04-15 | 8 | In Progress
2 | Phase 2: Strategy Development | 2024-04-16 | 2024-05-15 | 30 | In Progress
2.1 | Define Strategic Goals | 2024-04-16 | 2024-04-30 | 15 | In Progress
2.2 | Develop Action Plans | 2024-05-01 | 2024-05-15 | 15 | To Do
3 | Phase 3: Implementation Planning | 2024-05-16 | 2024-06-15 | 31 | To Do
3.1 | Resource Allocation | 2024-05-16 | 2024-05-31 | 16 | To Do
3.2 | Create Timeline & Milestones | 2024-06-01 | 2024-06-15 | 15 | To Do
M1 | End of Phase 2 Review | 2024-05-15 | 2024-05-15 | 1 | Milestone Achieved
M2 | Final Strategy Approval | 2024-06-15 | 2024-06-15 | 1 | To Do (Future)
© 2024 Office Use Strategy Planning Template ¦ Gantt Chart Format