## Worksheet
Strategy Planning Gantt Chart - One Page Template
Task / Activity | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
Initiate Strategy Planning Phase | ● |  |  |  |  | Q1 Complete
Market & Competitor Analysis | ●●●● | [5 empty] | End Mar 2025
Internal Assessment & SWOT | ●●● | [5 empty] | End Feb 2025
Define Strategic Objectives | ● | ●●●● | [5 empty] | End Apr 2025
Develop Strategic Initiatives | ● | ●●●● | [5 empty] | End Apr 2025
Resource Allocation & Budgeting | ● | ●●●● | [5 empty] | End Apr 2025
Stakeholder Alignment Meeting | ●●● |  |  |  | ● |  | Mid Apr 2025
Finalize Strategy Document | ●●● |  |  |  | ● |  | Mid Apr 2025
Leadership Approval & Sign-off | ●●●● |  |  |  |  | End May 2025
Rollout Planning & Communication | ● | ●●●● | [5 empty] | End Jun 2025
Q3 Strategy Implementation Kickoff | ● | ●●●● | [5 empty] | Start Jul 2025
Progress Review & Adjustment (Mid-Year) | ● | ●●●● | [5 empty] | Mid Aug 2025
Annual Strategy Review & Future Planning | ● | ●●●● | [5 empty] | End Dec 2025
Legend:● = Progress ¦ QX Complete = Quarter End ¦ Mid X = Mid-month