## Worksheet
Strategy Planning - Gantt Chart (Planning View)
Task ID | Task Name | Start Date | End Date | Status | Jan '24 | Feb '24 | Mar '24 | Apr '24 | May '24 | Jun '24 | Jul '24 | Aug '24 | Sep '24 | Oct '24 | Nov '24 | Dec '24
T001 | Initiate Strategy Development | 2024-01-05 | 2024-01-31 | In Progress | █
T002 | Market Research & Analysis | 2024-01-15 | 2024-03-31 | In Progress | █ |  |  |  |  | █
T003 | Competitor Benchmarking | 2024-02-15 | 2024-04-15 | In Progress | [6 empty] | █ |  |  | █
T004 | Stakeholder Alignment Workshop | 2024-03-10 | 2024-03-15 | Completed | [6 empty] | █
T005 | Strategy Finalization & Approval | 2024-04-16 | 2024-06-30 | Not Started | [7 empty] | █
M001 | Strategy Approval Sign-Off | 2024-06-30 | 2024-06-30 | Milestone | ●
T006 | Implementation Kickoff Plan | 2024-07-01 | 2024-12-31 | Not Started | [6 empty] | █ |  |  | █
T007 | Quarterly Review & Adjustments (Q3) | 2024-09-15 | 2024-11-30 | Not Started | [9 empty] | █
T008 | Final Evaluation & Reporting | 2024-12-15 | 2024-12-31 | Not Started | [9 empty] | █