## Worksheet
Task | Timeline (Months)
| Jan | Feb | Mar | Apr | May | Jun | Jul | Sep | Oct
Phase 1: Initiation | bar: Timeline (Months) Jan to Timeline (Months) Feb
Define Strategic Objectives | Timeline (Months) Jan: 100%
Stakeholder Engagement Workshop | Timeline (Months) Jan: 50%
Phase 2: Strategic Planning | bar: Timeline (Months) Jan to Timeline (Months) Jun
SWOT Analysis & Market Research | Timeline (Months) Feb: 75%
Develop Strategic Framework | Timeline (Months) Mar: 80%
Phase 3: Implementation | bar: Timeline (Months) Jan to Timeline (Months) Oct
Resource Allocation & Team Setup | Timeline (Months) Feb: 90%
Project Rollout Phase 1 | Timeline (Months) Mar: 60%
Project Rollout Phase 2 | Timeline (Months) Apr: 40%
Strategic Launch (Milestone) | bar: Timeline (Months) May
Report Version - Strategy Planning Gantt Chart ¦ Updated as of May 2025