## Worksheet
Startup Strategy Planning Gantt Chart
Task / Milestone | Start Date | End Date | Timeline View
Market Research & Validation | 2024-04-01 | 2024-05-15
Product Roadmap Definition | 2024-05-16 | 2024-06-30
Prototype Development | 2024-07-01 | 2024-08-31
Alpha Testing & Feedback | 2024-09-01 | 2024-10-15
Seed Funding Round | 2024-10-16 | 2024-11-30
Full Product Launch | 2024-12-01 | 2024-12-31
Key Milestone: MVP Release | 2024-10-31 | 2024-10-31
Key Milestone: First 1,000 Users | 2024-12-15 | 2024-12-15