## Worksheet
Team Use Gantt Chart – Strategy Planning
Task / Phase | Owner | Start Date | End Date | Status | Progress (%)
Phase 1 – Strategic Planning
Define Objectives & Vision | Jane Doe (PM) | 2024-04-01 | 2024-04-15 | In Progress
Conduct SWOT Analysis | Mark Lee (Analyst) | 2024-04-16 | 2024-04-30 | To Do
Phase 2 – Strategy Development
Develop Action Plan | Jane Doe (PM) | 2024-05-01 | 2024-05-15 | To Do
Assign Team Roles & Responsibilities | Anna Kim (HR) | 2024-05-16 | 2024-05-31 | To Do
Phase 3 – Implementation
Begin Pilot Campaign | Tom Wright (Marketing) | 2024-06-01 | 2024-06-30 | To Do
Final Strategy Review Meeting | Jane Doe (PM) | 2024-07-15 | 2024-07-15 | Milestone
Phase 4 – Review & Optimization
Collect Feedback & Metrics | Anna Kim (HR) | 2024-08-01 | 2024-08-15 | To Do
Finalize Strategy Report | Mark Lee (Analyst) | 2024-08-16 | 2024-08-31 | To Do
Last updated on April 1, 2024 ¦ For team use in strategy planning.