## Worksheet
Strategy Planning - Gantt Chart Template
Template Type:Gantt Chart
Style/Version:Template Version 1.0
Task Name | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Party
Define Strategic Goals | 2024-04-01 | 2024-04-15 | 15 | 95 | CEO & Leadership Team
MKT Research & Market Analysis | 2024-04-10 | 2024-05-15 | 36 | 75 | Marketing Department
SWOT Analysis & Risk Assessment | 2024-04-15 | 2024-05-10 | 26 | 65 | Strategy Team
Create Action Plan & Roadmap | 2024-05-11 | 2024-06-30 | 51 | 35 | Project Manager, Team Leads
Budget Allocation & Approval | 2024-06-01 | 2024-07-15 | 45 | 25 | Finance Team, Executive Board
Implementation Phase I (Pilot) | 2024-07-16 | 2024-09-30 | 76 | 15 | All Departments (Pilot Group)
Evaluate & Adjust Strategy | 2024-10-01 | 2024-10-31 | 31 | 5 | Strategy & Steering Committee
Note: This template is designed for planning and tracking strategic initiatives using a Gantt chart format. Adjust dates, tasks, and progress as needed.