## Worksheet
Strategy Planning - Gantt Chart (Tracking View)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
001 | Phase 1: Research & Analysis | 2024-04-05 | 2024-05-15 | 41 | In Progress | 68%
002 | Define Strategic Goals | 2024-05-16 | 2024-05-31 | 16 | In Progress | 85%
003 | Market Positioning & SWOT | 2024-06-01 | 2024-06-15 | 15 | In Progress | 73%
004 | Develop Action Plan | 2024-06-16 | 2024-07-31 | 55 | Not Started | 0%
005 | Resource Allocation & Budgeting | 2024-08-01 | 2024-08-31 | 31 | Not Started | 0%
M1 | Strategic Plan Finalized | 2024-08-31 | 2024-08-31 | 1 | Milestone | 100%
006 | Implementation Phase Kickoff | 2024-09-01 | 2024-11-30 | 91 | Not Started | 0%
007 | Quarterly Review & Adjustment | 2024-12-15 | 2024-12-31 | 17 | Not Started | 0%
Legend:In Progress (green), Not Started (gray), Milestone (yellow highlight).