## Worksheet
Strategy Planning - Home Template - Planning View
Objective / Initiative | Planning Timeline |  |  |  | Owner | Status | Priority
| Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024
Quarterly Strategic Goals and Initiatives
Launch New Product Line | Concept Development | Prototype Testing | Market Validation | Full Launch & Marketing Campaign | Sarah Johnson (Product) | In Progress | High
Key Performance Indicators (KPIs)
Customer Acquisition Cost (CAC) | Target: $45 | Target: $42 | Target: $39 | Target: $36 | Progress Tracking (Monthly)
Customer Retention Rate | Target: 80% | Target: 82% | Target: 85% | Target: 87% | Current Rate
Resource Allocation Overview
Marketing Budget (Q1-Q4) | $150K | $200K | $250K | $300K | Funding Source: Corporate Allocation
Risk Assessment & Mitigation
Market Competition Risk | Low Impact, Medium Likelihood | Mitigation: Competitive Analysis Monthly | Mitigation: Pricing Flexibility Strategy | Mitigation: Brand Differentiation Campaigns | Risk Owner: Alex Rivera (Strategy)
Strategic Milestones Summary
Milestone 1: Finalize Product Roadmap | Due: Mar 31, 2024 |  |  |  | Product Team | Not Started | High
Milestone 2: Complete First Beta Test Group Feedback Cycle | Due: Jun 30, 2024 |  |  |  | Product & UX Teams | Not Started | High
Next Review Date: May 15, 2024 ¦ Prepared by: Strategy Planning Office