## Worksheet
Monthly Strategy Planning Dashboard - Client View
Week | Key Objective | Action Item | Owner | Status | Due Date | Budget (USD) | Risk Level | Milestone Achieved? | Notes/Comments
Week 1 (Oct 1–7) | Market Positioning Strategy | Conduct competitive analysis | Jane Doe - Marketing Lead | In Progress | Oct 5, 2024 | $1,800 | Medium | No | Data collection in progress; results expected by Oct 3.
Week 2 (Oct 8–14) | Campaign Development | Create initial campaign concepts | Mark Lee - Creative Director | Pending | Oct 12, 2024 | $3,500 | Low | No | Waiting on market research findings.
Week 3 (Oct 15–21) | User Engagement Plan | Design UX improvements for app | Alex Chen - Product Manager | In Progress | Oct 20, 2024 | $5,000 | High | No | Prototype design phase underway.
Week 4 (Oct 22–31) | Digital Advertising Launch | Set up Google Ads and Meta campaigns | Sarah Kim - Digital Lead | Pending | Oct 25, 2024 | $8,000 | Medium | No | Waiting on approved creatives from Creative Team.
Monthly Summary Metrics |  |  | Total Tasks: 4 ¦ Completed: 0 ¦ In Progress: 2 ¦ On Hold: 2 | Planned Budget: $18,300 | Actual Spend (So Far): $6,300 | Overall Status: On Track
Notes:Monthly planning review scheduled for October 30, 2024. All stakeholders to provide updates by end of week. Feedback on current strategy alignment to be documented and reviewed.