## Worksheet
Monthly Strategy Planning Dashboard
Manager View - October 2024
Objective | Key Results (KRs) |  |  |  |  | Owner | Status
| Target | Current Progress | Weight (%) | Deadline | Action Items (Weekly)
Launch Q4 Product Suite | Deliver 3 new features | 3/3 completed | 40% | Oct 15, 2024 | - Week 1: Finalize UI mockups - Week 3: Beta testing starts - Week 5: Release deployment | Product Team | Completed
| Implement customer feedback integration | 100% of feedback processed | 40% |  |  | Oct 30, 2024
Increase Customer Retention Rate | Reduce churn by 15% | 10% achieved | 30% | Nov 5, 2024
| Launch loyalty program for active users | 87% of target users enrolled | 35% |  | - Week 1: Survey customer segments - Week 2: Design rewards tiers - Week 4: Pilot launch with top clients
| Improve onboarding experience score | From 3.8 to 4.5 avg rating | 40%
Optimize Sales Pipeline Efficiency | Reduce sales cycle time by 20% | 13% achieved | 30% | Nov 10, 2024
| Implement CRM automation tools | 7/10 modules deployed | 55% |  | - Week 1: Audit current process - Week 3: Deploy first automation - Week 6: Full rollout
Monthly Progress Summary | [5 empty] | 12/14 KRs in progress | In Progress