## Worksheet
Monthly Strategy Planning - Summary View
Month: October 2024 |  | Planning Period: 01/10/2024 - 31/10/2024
Objective / Goal | KPI Target | Actual Results | Status | Notes & Actions
1. Increase Customer Retention Rate by 8%
Customer Retention Goal | 8% increase | 6.4% | On Track (80%) | Pilot loyalty program; additional feedback survey sent.
2. Launch New Product Line by Mid-Month
New Product Release | Complete by 15/10/2024 | Completed on 13/10/2024 | On Schedule | Marketing campaign initiated. Pre-orders open.
3. Improve Team Productivity by 10%
Team Efficiency Index | 10% improvement | 9.2% improvement | On Track (92%) | Training sessions completed; tools updated.
4. Expand into Two New Markets by Month-End
Market Expansion | 2 new markets (Germany, Brazil) | 1 market live (Germany); Brazil in final approval | Delayed (50%) | Legal clearance delayed; plan to resolve by 25/10.
Overall Performance Summary | 3 out of 4 key goals on track. One delayed due to external approvals. Focus: Accelerate Brazil market launch and finalize retention plan.