## Worksheet
Strategy Planning - Extended Planner Template
Phase / Milestone | Objective / Goal | Timeline & Execution Plan |  |  |  | Responsible Team/Person | Status
|  | Start Date | End Date | Duration (weeks) | KPIs / Success Indicators
Phase 1: Strategic Assessment & Research
Market Analysis | Identify market trends, opportunities, and threats using SWOT/PESTEL analysis | 2024-04-01 | 2024-05-15 | 7 | Comprehensive report with 8+ key insights and data sources cited | Market Research Team | In Progress
Competitor Benchmarking | Evaluate top 5 competitors’ strategies, strengths, and weaknesses | 2024-05-16 | 2024-06-15 | 5 | Benchmarking matrix completed with scorecard and recommendations | Competitive Intelligence Unit | Pending
Phase 2: Goal Setting & Strategy Development
Define Strategic Vision & Mission | Establish long-term vision and mission statement aligned with core values | 2024-06-16 | 2024-07-31 | 7 | Vision and mission approved by leadership team with stakeholder input | C-Suite & Strategy Board | Pending
Set 3-5 Strategic Goals (2025-2027) | Develop measurable, time-bound goals supporting long-term growth | 2024-08-01 | 2024-10-31 | 13 | All goals have SMART criteria and KPIs defined | Strategic Planning Committee | Pending
Phase 3: Implementation & Execution Planning
Develop Action Plans (by Goal) | Create detailed roadmaps with tasks, owners, milestones, and dependencies | 2024-11-01 | 2025-01-31 | 14 | Each goal has a fully populated action plan with 95% task coverage | Action Plan Leads (Department Heads) | Pending
Resource Allocation & Budgeting | Assign budget, personnel, tools, and technology needed for execution | 2025-02-01 | 2025-03-31 | 8 | Budget approved with 98% alignment to action plans and financial controls in place | Finance & HR Departments | Pending
Phase 4: Monitoring, Review & Adaptation
Establish Governance Framework | Set up steering committee, review cadence, and escalation protocols | 2025-04-01 | 2025-04-30 | 4 | Governance structure documented with clear roles and meeting schedule defined | Executive Office | Pending
Quarterly Review & Adjustment Cycles | Conduct formal reviews every quarter to assess progress and adapt strategies | 2025-05-01 | Ongoing (Annual Cycle) | N/A | Review reports submitted on time with documented adjustments for 4 quarters | Strategy Team & Steering Committee | Pending
Total Duration: ~18 Months (2024-04-01 to 2025-12-31) |  | Start Date: Apr 1, 2024 | End Date: Dec 31, 2025 | Total Weeks: ~78 | Template Version: Extended ¦ Created for Strategy Planning Use
Note: This planner is designed for dynamic use—update statuses, KPIs, and timelines regularly. Use color coding in Excel to visualize progress.