## Project Plan - Analysis View
Project Plan - Analysis View
Purpose:Strategy Planning
Phase / Milestone | Key Activities | Responsible Team/Person | Start Date | End Date | Status | Risk Level
Phase 1: Project Initiation
Project Charter Approval | Define project scope, goals, and stakeholders. | Project Manager | 2024-01-05 | 2024-01-15 | In Progress | Low
Phase 2: Strategy & Resource Planning
Market Analysis & Competitor Review | Conduct SWOT, PESTEL, and competitive benchmarking. | Business Analysts | 2024-01-16 | 2024-01-31 | To Do | Medium
Risk Assessment & Mitigation Plan | Identify risks, assign probabilities and impacts. | Risk Manager | 2024-01-16 | 2024-01-31 | To Do | Medium
Phase 3: Strategy Execution & Monitoring
Resource Allocation & Budget Setup | Assign team members and finalize budget. | Finance & HR Teams | 2024-02-01 | 2024-02-15 | To Do | Low
Phase 4: Performance & Review
Mid-Project Review & KPI Tracking | Evaluate progress against planned milestones. | Project Manager, Steering Committee | 2024-03-01 | 2024-03-15 | To Do | Low
Phase 5: Project Closure & Lessons Learned
Final Reporting & Stakeholder Presentation | Deliver project outcomes and feedback summary. | Project Manager, Communications Lead | 2024-04-01 | 2024-04-15 | To Do | Low
Note: This template is designed for strategic planning and analysis. Adjust dates, teams, and statuses as needed.