## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority
1 | Define Project Scope | Project Manager | 2023-10-01 | 2023-10-05 | Completed | High
2 | Develop Strategy Framework | Strategy Lead | 2023-10-06 | 2023-10-15 | In Progress | High
3 | Conduct Market Research | Research Analyst | 2023-10-16 | 2023-10-25 | Not Started | Medium
4 | Design Implementation Plan | Operations Manager | 2023-10-26 | 2023-11-05 | Not Started | High
5 | Review & Approve Plan | Executive Team | 2023-11-06 | 2023-11-10 | Not Started | Critical
Total Tasks: | [5 empty] | 5