## Worksheet
Project Plan - Strategy Planning
Data Version ¦ Purpose: Strategy Planning ¦ Template Type: Project Plan
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
T001 | Define Project Objectives | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | 75%
T002 | Stakeholder Analysis | Business Analyst | 2023-10-06 | 2023-10-15 | To Do | 0%
T003 | Market Research & Competitor Analysis | Research Lead | 2023-10-16 | 2023-10-31 | To Do | 0%
T004 | Develop Strategic Framework | Strategy Director | 2023-11-01 | 2023-11-15 | To Do | 0%
T005 | Resource Planning & Budgeting | Finance Manager | 2023-11-16 | 2023-11-30 | To Do | 0%
Total Project Duration: | [5 empty] | 30 days