## Worksheet
STRATEGY PLANNING PROJECT PLAN
Task ID | Task Name | Description | Responsible Party | Start Date | End Date | Duration (Days) | Status | Notes
P001 | Define Strategic Objectives | Identify long-term goals and key success factors for the organization. | CEO & Executive Team | 2024-01-05 | 2024-01-15 | 11 | Completed | Aligned with market analysis and stakeholder feedback.
P002 | SWOT Analysis | Evaluate internal strengths and weaknesses, external opportunities and threats. | Strategy Department | 2024-01-16 | 2024-01-30 | 15 | In Progress | Final review scheduled for 01/28.
P003 | Market Research & Trend Analysis | Gather and analyze current market data, customer trends, and competitor strategies. | Marketing Team | 2024-01-18 | 2024-02-15 | 29 | In Progress | Phase 1 completed; Phase 2 underway.
P004 | Develop Strategic Initiatives | Create detailed action plans for achieving objectives. | Strategy & Operations | 2024-02-16 | 2024-03-15 | 30 | Not Started | Dependent on market research completion.
P005 | Risk Assessment & Mitigation Planning | Identify potential risks and develop response strategies. | Risk Management Team | 2024-03-16 | 2024-03-31 | 16 | Not Started | Requires input from all departments.
P006 | Resource Allocation Planning | Determine budget, personnel, and tools required for each initiative. | Finance & HR Departments | 2024-03-18 | 2024-04-15 | 28 | Not Started | Budget approvals pending.
P007 | Project Plan Approval & Sign-Off | Presentation and formal approval by executive leadership. | Project Manager & CEO | 2024-04-16 | 2024-04-30 | 15 | Not Started | Final review meeting scheduled for 04/28.
P008 | Launch & Implementation Phase | Begin execution of approved strategic initiatives. | All Project Teams | 2024-05-01 | 2024-11-30 | 213 | Not Started | Phased rollout by department.
Total Tasks: | [7 empty] | 8