## Employee View - Project Plan
Employee Name | Role | Project Task | Start Date | Due Date | Status | Progress (%)
Sarah Johnson | Project Manager | Strategy Alignment Workshop | 2024-04-01 | 2024-04-15 | In Progress | 65%
James Wilson | UX Designer | User Flow Diagrams | 2024-04-03 | 2024-04-18 | In Progress | 55%
Linda Chen | Frontend Developer | UI Component Implementation | 2024-04-05 | 2024-05-10 | Completed | 100%
Michael Brown | Backend Developer | API Integration Setup | 2024-04-07 | 2024-05-15 | In Progress | 70%
Emily Davis | Quality Analyst | Test Case Development | 2024-04-10 | 2024-05-17 | Delayed | 35%
Robert Taylor | Marketing Specialist | Campaign Launch Plan | 2024-04-12 | 2024-05-18 | In Progress | 45%