## Worksheet
Project Plan - Strategy Planning (Extended Version)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete | Budget (USD) | Risk Level | Milestone/Notes
Phase 1: Strategy Initiation (Q1)
STR-001 | Define strategic objectives and KPIs | Exec Team & Planning Office | 2024-01-05 | 2024-01-31 | Completed | 100% | $25,000 | Low | Approved by Board of Directors
STR-002 | Conduct SWOT analysis and market assessment | Market Research & Strategy Team | 2024-01-15 | 2024-02-15 | Completed | 100% | $32,500 | Medium | Published internal report
Phase 2: Planning & Development (Q2)
PLN-001 | Develop high-level project roadmap | Project Management Office | 2024-03-01 | 2024-03-31 | Completed | 100% | $18,750 | Low | Roadmap approved by C-suite
PLN-002 | Define project phases and deliverables | Planning Team & Stakeholders | 2024-03-15 | 2024-04-15 | Completed | 100% | $22,800 | Medium | Finalized with change control board
Phase 3: Resource Allocation (Q2-Q3)
RES-001 | Assign project managers and core team members | Hiring & HR Department | 2024-04-01 | 2024-05-31 | Delayed | 65% | $48,000 | High | Key roles pending approval from finance
Phase 4: Implementation Planning (Q3)
IMP-001 | Create detailed implementation timeline | Project Management Office | 2024-06-15 | 2024-07-31 | Completed | 100% | $24,500 | Low | Scheduled for quarterly review
Phase 5: Risk & Compliance (Ongoing)
RISK-001 | Finalize risk mitigation strategy | Risk Management Team | 2024-07-15 | 2024-08-31 | Completed | 100% | $20,350 | Medium | Mitigation plan approved and documented
Phase 6: Review & Final Approvals (Q4)
REV-001 | Conduct stakeholder review workshop | Planning & Stakeholder Engagement | 2024-10-15 | 2024-11-30 | Completed | 100% | $28,950 | Low | All feedback incorporated
Final Deliverables & Project Approval (Q4)
FINAL-001 | Submit final strategy plan for executive approval | Executive Planning Office | 2024-12-01 | 2024-12-31 | Delayed (Pending) | 85% | $15,000 | High | Final review scheduled for Dec. 20th
Summary: Total Budget & Timeline Overview | [7 empty] | Total Budget:$319,650 Duration:Jan 2024 - Dec 2024 (12 months) Status Overview:7/8 tasks complete, 1 delayed critical path