## Financial View - Project Plan
Financial View - Project Plan
Strategy Planning ¦ Project Plan Template ¦ Financial Perspective
Phase / Milestone | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (USD) | % Budget Used | Status
Project Initiation | 2024-01-05 | 2024-01-31 | $50,000 | $48,500 | $-1,500 | 97% | On Track
Market Research & Analysis | 2024-02-01 | 2024-03-15 | $75,000 | $76,895 | $1,895 | 102.5% | At Risk
Product Development Phase 1 | 2024-03-16 | 2024-06-30 | $350,000 | $98,755 | $-251,245 | 28.2% | On Track
Testing & Quality Assurance | 2024-07-01 | 2024-08-31 | $85,000 | $85,936 | $936 | 101.1% | At Risk
Marketing & Launch Campaign | 2024-09-01 | 2024-10-31 | $150,000 | $78,456 | $-71,544 | 52.3% | On Track
Total | $710,000 |  |  | $488,542 | $-221,458 | 68.8%
Note: All figures in USD. Variance = Actual Spend - Budget. Status based on spending efficiency and timeline adherence.