## Worksheet
Freelancer Project Plan - Strategy Planning
Project Overview
Phase / Task | Start Date | End Date | Responsible Person | Status | Budget (USD) | Milestones & Deliverables"
Project Initiation & Kickoff | 2024-04-01 | 2024-04-05 | Jane Doe (Lead) | In Progress | $1,500 | Project charter, stakeholder list, initial plan document
Market & Competitor Research | 2024-04-06 | 2024-04-15 | Mike Lee (Research) | Pending | $800 | Competitor analysis, SWOT report, market trends document
Strategic Objective Development | 2024-04-16 | 2024-04-25 | Alice Smith (Strategy) | Pending | $1,200 | 3–5 core strategic goals with KPIs, roadmap draft
Resource Allocation & Team Setup | 2024-04-26 | 2024-05-10 | John Brown (Ops) | Pending | $1,800 | Roster of team members, roles & responsibilities matrix
Implementation Planning & Schedule | 2024-05-11 | 2024-05-31 | Sarah Kim (Project Manager) | Pending | $2,500 | Gantt chart, milestone calendar, risk assessment document
Review & Approval by Stakeholders | 2024-06-01 | 2024-06-15 | All Key Stakeholders | Pending | $500 | Finalized strategy plan, formal sign-off document
Total Estimated Budget: $8,300