## Worksheet
Large Business Project Plan - Strategy Planning
Phase | Task Name | Description | Responsible Team/Person | Start Date | End Date | Status | Budget (USD)
Phase 1: Strategic Assessment
1.1 | Market & Competitive Analysis | Comprehensive review of industry trends, customer needs, and competitor positioning. | Strategy Division | 2024-04-01 | 2024-05-15 | In Progress | $45,000
1.2 | Milestone: Finalize Market Insights Report | Deliver complete analysis and executive summary. | Strategy Lead, Jane Doe | 2024-05-15 | 2024-05-15 | Completed | $0
Phase 2: Goal & Objective Setting
2.1 | Define Strategic Objectives (3-Year Horizon) | Set measurable KPIs aligned with corporate vision. | C-Suite Team | 2024-05-16 | 2024-06-15 | In Progress | $30,000
2.2 | Milestone: Approve 3-Year Strategic Roadmap | Leadership approval of final strategic goals. | CEO & Board Review Committee | 2024-06-15 | 2024-06-15 | Pending | $0
Phase 3: Initiative Planning
3.1 | Develop Project Initiatives (Top 5) | Identify and detail priority projects to achieve strategic objectives. | Project Management Office | 2024-06-16 | 2024-07-31 | To Do | $85,000
Phase 4: Resource Allocation & Budgeting
4.1 | Resource Planning (Human, Tech, Facilities) | Assess team capacity and technology requirements. | HR & IT Departments | 2024-07-01 | 2024-07-31 | To Do | $65,000
4.2 | Milestone: Finalize Annual Strategic Budget (Q3) | Submit approved budget to Finance for Q3 release. | CFO & Strategy Team | 2024-07-31 | 2024-07-31 | To Do | $0
Phase 5: Communication & Rollout
5.1 | Internal Stakeholder Briefing Sessions | Present strategy to all department heads and managers. | Corporate Communications | 2024-08-01 | 2024-08-15 | To Do | $15,000
5.2 | Milestone: Official Strategy Launch Event | Company-wide launch with leadership presentation. | CEO, CMO, Communications Team | 2024-08-15 | 2024-08-15 | To Do | $75,000
Total Estimated Budget: | [6 empty] | $315,000
This document is part of the Large Business Project Plan - Strategy Planning. Version 1.0 ¦ Prepared on May 5, 2024