## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Budget (USD)
Project Initiation & Planning | Jane Smith | 2024-01-05 | 2024-01-15 | Completed | High | 15,000
Market Research & Analysis | Mark Johnson | 2024-01-16 | 2024-01-31 | In Progress | High | 8,500
Strategy Development Workshop | Sarah Lee | 2024-02-01 | 2024-02-15 | To Do | High | 6,300
Resource Allocation & Team Setup | David Brown | 2024-02-16 | 2024-03-15 | To Do | Medium | 18,750
Risk Assessment & Mitigation Plan | Linda Chen | 2024-03-16 | 2024-03-31 | To Do | High | 5,200
Phase 1 Launch Preparation | Alex Turner | 2024-04-01 | 2024-04-30 | To Do | Medium | 35,500
Milestone Review & Adjustments | Jane Smith | 2024-05-15 | 2024-05-31 | To Do | High | 7,800
Full Project Review & Closeout | Mark Johnson | 2024-06-15 | 2024-06-30 | To Do | Medium | 9,100