## Worksheet
Project ID | Project Name | Start Date | End Date | Status | Owner
PJ-001 | Innovation Roadmap 2024-2026 | Jan 15, 2024 | Dec 31, 2026 | In Progress | Jane Smith
PJ-002 | Digital Transformation Initiative | Mar 10, 2024 | Jun 30, 2025 | Planning | Robert Johnson
PJ-003 | Customer Experience Enhancement | Planned for Q3 2024 - Q1 2025 |  |  |  | Sarah Lee
PJ-004 | Global Expansion Strategy | Q1 2025 - Q4 2026 |  |  |  | David Kim
Phase | Milestone | Target Date | Responsible Team | Status
Initiation | Project Charter Approval | Jan 31, 2024 | Strategy Office | Completed
Planning | Risk Assessment Report Finalized | Mar 15, 2024 |  |  | Pending Review
Execution | Phase 1 Launch: Product Redesign | Jun 30, 2024 | Product Team | Pending Initiation
Monitoring & Controlling | Monthly Performance Review Complete (Q1) | Mar 31, 2024 |  |  | Completed
Closing | Final Project Report Submission | Dec 15, 2026 |  |  | Pending Planning
Resource Type | Role/Position | Personnel Assigned | Hours Allocated (Monthly) | Budget Allocated ($)
Labor | Project Manager | Jane Smith | 160 | 24,000
Labor | Business Analysts (x2) | Alex Turner, Maria Gonzalez |  | 38,400
Technology | Software Licenses & Tools | JIRA, Confluence, MS Project Pro |  | 12,000
Training & Development | Cross-functional Workshops | 4 sessions (Q2-Q3 2024) |  | 8,500
Total Allocated Budget: |  |  |  | 82,900
KPI Category | KPI Name | Target Value | Measurement Frequency | Status Tracking
Timeline Performance | On-Time Delivery Rate (%) | 95% | Monthly | In Progress (87%)
Budget Adherence | Budget Variance (% of Total) |  | Target: ≤5%
Stakeholder Satisfaction | Survey Score (1-10 scale) | 8.5 | Quarterly | Pending First Survey
Innovation Impact | New Features Delivered (per Quarter) |  | Target: 4 per quarter
Risk Management | Open Risks Below Threshold (Max 5) | ≤5 | Bi-weekly | Pending Review
Risk ID | Description | Probability (Low/Med/High) | Impact (Low/Med/High) | Response Strategy
RK-001 | Key team member may leave during Phase 2 | Medium | High | Develop succession plan; cross-train backup staff
RK-002 | Third-party vendor delay in API integration | High | Medium | Negotiate SLA; identify alternative provider
RK-003 | Regulatory changes affecting digital rollout timeline | High Impact, High Probability |  | Monitor legislation; engage legal counsel monthly
RK-004 | Customer adoption rate below forecast in pilot phase | Medium | High | Conduct usability testing; revise user onboarding process
Issue Log (Active)
I-001 | Delayed software testing environment setup | High | Mitigation: Fast-track infrastructure request; assign dedicated IT coordinator
I-002 | Stakeholder disagreement on feature prioritization | Medium | Resolution: Facilitate steering committee workshop; align on roadmap priorities
Section | Description & Action Items
Next Review Meeting | Date: Apr 5, 2024 ¦ Time: 10:00 AM ¦ Location: Conference Room B Agenda items: - Phase 1 progress report - Budget review for Q2 - Risk mitigation update
Immediate Actions | - Finalize risk register by Mar 30, 2024 - Confirm vendor SLAs with legal team by Apr 15, 2024 - Schedule first stakeholder survey (target: May 1, 2024)
Long-Term Initiatives | - Establish project governance committee (Q3) - Implement automated KPI dashboard (Q3) - Begin talent development program for project staff (Q4)
Approved By:
Signature | ________________________________________
Name | David Chen, VP Strategy & Innovation
Date: Apr 1, 2024