## Worksheet
Project Plan - Strategy Planning
Phase | Task | Owner | Start Date | End Date | Status
Phase 1: Strategy Development | Define project objectives and goals | John Smith | 2024-03-01 | 2024-03-15 | In Progress
| Identify key stakeholders and roles | Jane Doe | 2024-03-16 | 2024-03-25 | Pending Review
| Conduct market and competitor analysis | Alex Johnson | 2024-03-26 | 2024-04-10 | Not Started
| Create initial strategy draft for review | Sarah Lee | 2024-04-11 | 2024-04-15 | Not Started
Phase 2: Resource Allocation | Assess resource requirements (budget, personnel) | Robert Brown | 2024-04-16 | 2024-04-30 | In Progress
| Allocate team members to key activities | Lisa Chen | 2024-05-01 | 2024-05-15 | Not Started
| Approve budget and finalize project plan | Michael Torres | 2024-05-16 | 2024-05-31 | Not Started
Phase 3: Execution & Monitoring | Initiate project kickoff meeting | Alice Parker | 2024-06-01 | 2024-06-15 | Not Started
| Execute core project activities (bi-weekly) | All Team Members | 2024-06-16 | 2024-08-31 | Not Started
| Milestone review and progress reporting (monthly) | Project Manager | 2024-07-15, 2024-08-15 | 2024-08-31 | Not Started
Phase 4: Project Closure | Finalize deliverables and documentation | Daniel Kim | 2024-09-01 | 2024-09-15 | Not Started
| Conduct post-project review and lessons learned session | Sophia Martinez | 2024-09-16 | 2024-09-30 | Not Started
| Cease project activities and release resources | All Team Members | 2024-10-01 | 2024-10-15 | Not Started
Note: This is a sample project plan template designed for office use in strategic planning. Status updates should be reviewed weekly.