## Worksheet
Strategy Planning - Project Plan (One Page)
# | Task / Activity | Owner | Start Date | Due Date | Status | Notes / Comments
1 | Define Project Vision and Objectives | Project Manager | 2024-04-01 | 2024-04-15 | In Progress | Align with executive leadership and stakeholders.
2 | Conduct Market and Competitor Analysis | Market Analyst | 2024-04-16 | 2024-04-30 | Not Started | Data collection and benchmarking required.
3 | Identify Key Success Factors (KSF) | Strategy Lead | 2024-05-01 | 2024-05-10 | Not Started | Review past project outcomes.
4 | Develop Strategy Framework & Roadmap | Strategy Team | 2024-05-11 | 2024-05-31 | Not Started | Include milestones and dependencies.
5 | Secure Leadership Approval & Budget | CFO / Executive Team | 2024-06-01 | 2024-06-15 | Not Started | Budget proposal to be submitted by Strategy Lead.
6 | Communicate Plan to Stakeholders | Project Manager | 2024-06-16 | 2024-06-30 | Not Started | Present via workshop and documentation.
7 | Begin Phase 1 Implementation | Implementation Team | 2024-07-01 | 2024-08-31 | Not Started | Execution phase begins post approval.
Last Updated:April 5, 2024 ¦Status Report:Live Tracking