## Worksheet
Strategy Planning - Project Plan
Template Type:Project Plan ¦Style/Version:Personal Use
Task ID | Task Name | Responsible Person | Timeline |  |  | Status
|  |  | Start Date | Due Date | Duration (days)
T001 | Define Project Goals | John Doe | 2024-04-15 | 2024-04-18 | 3 | In Progress
T002 | Conduct Market Research | Jane Smith | 2024-04-19 | 2024-04-30 | 11 | Pending
T003 | Create Strategy Framework | Mike Johnson | 2024-05-01 | 2024-05-10 | 9 | Not Started
T004 | Develop Action Plan | Sarah Lee | 2024-05-11 | 2024-05-20 | 9 | Not Started
T005 | Review & Finalize Plan | John Doe | 2024-05-21 | 2024-05-23 | 3 | Not Started