## Project Plan - Planning View
Project Plan - Planning View
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
P001 | Define Project Vision & Objectives | John Doe | 2024-04-01 | 2024-04-15 | Completed | 100%
P002 | Conduct Market Research | Jane Smith | 2024-04-16 | 2024-05-15 | In Progress | 75%
P003 | Identify Key Stakeholders | Mike Johnson | 2024-04-16 | 2024-05-15 | In Progress | 60%
P004 | Develop Strategic Framework | Sarah Lee | 2024-05-16 | 2024-06-30 | Pending | 5%
P005 | Secure Executive Approval | David Brown | 2024-07-01 | 2024-07-15 | Pending | 0%
P006 | Create Implementation Roadmap | Emily Davis | 2024-07-16 | 2024-08-31 | Pending | 0%