## Worksheet
STRATEGY PLANNING - PROJECT PLAN
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
P001 | Define Project Objectives | Jane Smith | 2024-04-01 | 2024-04-05 | In Progress | 75%
P002 | Conduct Market Analysis | Michael Brown | 2024-04-06 | 2024-04-15 | To Do | 10%
P003 | Develop Strategy Framework | Sarah Johnson | 2024-04-16 | 2024-04-30 | To Do | 5%
P004 | Stakeholder Alignment Workshop | David Lee | 2024-05-01 | 2024-05-15 | To Do | 0%
P005 | Finalize Strategy Document | Jane Smith | 2024-05-16 | 2024-05-31 | To Do | 0%
Project Progress: | [5 empty] | 34%