## Project Plan - Report Version
Project Plan - Report Version
Phase/Task | Start Date | End Date | Status | Responsible Team/Person | Description
Project Initiation | 2024-01-05 | 2024-01-15 | In Progress | Project Manager, Team A | Capture project scope, objectives, and stakeholders.
Requirements Gathering | 2024-01-16 | 2024-01-31 | Pending | Business Analysts, UX Team | Collect and document detailed functional and non-functional requirements.
Design Phase | 2024-02-01 | 2024-02-15 | Pending | UI/UX Designers, Architects | Create wireframes, prototypes, and technical design documents.
Development (Sprint 1) | 2024-02-16 | 2024-03-01 | Pending | Development Team, QA Lead | Implement core features based on design specs.
Testing and QA | 2024-03-02 | 2024-03-15 | Pending | QA Engineers, Dev Team | Execute test cases, report and resolve defects.
User Training & Documentation | 2024-03-16 | 2024-03-31 | Pending | Training Coordinator, Documentation Team | Prepare user guides and conduct training sessions.
Deployment & Go-Live | 2024-04-01 | 2024-04-15 | Pending | DevOps, Project Manager | Deploy system to production environment and monitor initial performance.
Post-Launch Review | 2024-04-16 | 2024-05-31 | Pending | All Stakeholders, Project Manager | Evaluate project success, collect feedback, and document lessons learned.
This project plan is designed for strategy planning and reporting purposes. Last updated on.