## Worksheet
Task | Start Date | End Date | Responsible | Status
Define Project Scope | 2023-10-01 | 2023-10-05 | Project Manager | Completed
Create Strategy Document | 2023-10-06 | 2023-10-15 | Strategy Lead | In Progress
Resource Allocation Planning | 2023-10-16 | 2023-10-20 | HR & Finance Team | Not Started
Risk Assessment & Mitigation Plan | 2023-10-21 | 2023-10-25 | Risk Manager | Not Started
Develop Project Timeline (Gantt) | 2023-10-26 | 2023-10-31 | Project Manager | Not Started
Stakeholder Approval Meeting | 2023-11-01 | 2023-11-03 | Project Sponsor | Not Started
Project Kickoff Meeting | 2023-11-06 | 2023-11-06 | All Team Members | Not Started