## Worksheet
Small Business Project Plan - Strategy Planning
Project: Market Expansion Initiative ¦ Period: Q1 2024
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
P001 | Market Research & Analysis | Jane Doe (Marketing) | 2024-01-05 | 2024-01-19 | In Progress | 75%
P002 | Competitor Benchmarking | Mike Smith (Strategy) | 2024-01-15 | 2024-01-31 | In Progress | 65%
P003 | Customer Persona Development | Sarah Lee (UX/Design) | 2024-01-20 | 2024-01-31 | Pending | 0%
P004 | Budget Planning & Approval | Tom Brown (Finance) | 2024-01-18 | 2024-01-31 | In Progress | 50%
P005 | Marketing Campaign Design | Jane Doe (Marketing) | 2024-02-01 | 2024-02-15 | Not Started | 0%
P006 | Website Localization (Language & UI) | Sarah Lee (UX/Design) | 2024-02-15 | 2024-03-15 | Not Started | 0%
Total Project Progress: | [5 empty] | 48%