## Worksheet
Week | Date Range | Objective | Key Activities | Responsible Team | Status | Notes
Week 1 | Jan 1 - Jan 7 | Define project scope and goals | Conduct stakeholder meetings, finalize objectives, draft project charter | Project Lead | Not Started | Initial alignment workshop scheduled
Week 2 | Jan 8 - Jan 14 | Develop strategy roadmap | Identify milestones, define deliverables, allocate resources | Strategy Team | In Progress | Review with leadership next week
Week 3 | Jan 15 - Jan 21 | Resource planning and team assignment | Assign roles, confirm availability, set up communication tools | HR & Project Manager | Not Started | Pending team availability confirmation
Week 4 | Jan 22 - Jan 28 | Kickoff and initial execution phase | Launch project, conduct kickoff meeting, begin first deliverables | Entire Project Team | Pending | Kickoff meeting scheduled for Jan 23
Week 5 | Jan 29 - Feb 4 | Monitor progress and adjust plan as needed | Weekly review, risk assessment, update timelines | Project Manager | To Do | First progress review due Feb 2
End of Weekly Plan - Review and Update Next Week