## Worksheet
Strategy Planning - Project Template
Business Use ¦ Template Type: Project Template
Phase | Objective | Key Activities | Responsible Team/Person | Timeline (Start - End) | Status
Phase 1: Strategy Initiation | Define strategic goals and vision alignment | - Conduct stakeholder interviews - Review market trends - Establish strategic objectives | Strategy Team Lead | 2024-01-01 - 2024-01-15 | In Progress
Phase 2: Market Analysis | Assess competitive landscape and market opportunities | - Perform SWOT analysis - Analyze customer segments - Evaluate industry trends | Market Research Team | 2024-01-16 - 2024-02-15 | Pending
Phase 3: Strategy Development | Develop actionable strategic plans and initiatives | - Draft strategic roadmap - Define KPIs and success metrics - Prioritize key initiatives | Strategic Planning Committee | 2024-02-16 - 2024-03-15 | Pending
Phase 4: Resource Allocation | Assign budget, personnel, and tools to strategic initiatives | - Prepare resource plan - Approve budget allocation - Assign team leads | Finance & HR Department | 2024-03-16 - 2024-04-15 | Pending
Phase 5: Implementation Planning | Build detailed execution plans and timelines | - Create Gantt charts - Develop communication plan - Set up monitoring framework | Project Management Office (PMO) | 2024-04-16 - 2024-05-15 | Pending
Phase 6: Review & Approval | Secure leadership sign-off on the final strategy plan | - Present draft strategy to executive team - Incorporate feedback - Finalize and approve document | Executive Leadership Team | 2024-05-16 - 2024-05-31 | Pending
Phase 7: Rollout & Monitoring | Execute strategy and track performance continuously | - Launch initiatives - Conduct monthly reviews - Adjust based on KPIs and feedback | All Project Teams | 2024-06-01 - Ongoing | Pending
Total Duration: |  |  |  |  | 2024-01-01 to Ongoing