## Worksheet
Task | Responsible | Start Date | End Date | Status
Define Project Goals | Project Manager | 01/10/2024 | 05/10/2024 | In Progress
Conduct Stakeholder Analysis | Team Lead | 06/10/2024 | 10/10/2024 | Not Started
Develop Strategy Framework | Strategy Team | 11/10/2024 | 18/10/2024 | In Progress
Review & Approve Plan | Executive Team | 19/10/2024 | 25/10/2024 | Not Started
Implement Initial Actions | Project Manager | 26/10/2024 | 31/10/2024 | Not Started