## Worksheet
Strategy Planning - Project Template - Data Version
Phase | Objective | Key Activities | Responsible Party | Status | Start Date | End Date
Initiation | Define project scope and goals | Stakeholder interviews, vision alignment sessions | Project Manager | In Progress | 2024-01-05 | 2024-01-15
Analysis | Assess market, internal capabilities, and risks | Data collection, SWOT analysis, competitor benchmarking | Strategy Analysts | Pending | 2024-01-16 | 2024-01-31
Planning | Create detailed action plans and KPIs | Develop roadmap, assign milestones, set success metrics | Strategy Team Lead | To Do | 2024-02-01 | 2024-02-15
Execution | Implement strategic initiatives according to plan | Resource allocation, team coordination, progress tracking | All Project Teams | To Do | 2024-02-16 | 2024-05-31
Monitoring & Evaluation | Evaluate performance and adapt as needed | Monthly reviews, KPI tracking, feedback loops | Project Manager & Steering Committee | To Do | 2024-03-01 | 2024-06-30
Closure | Finalize deliverables and document lessons learned | Project review, report finalization, knowledge transfer | Project Manager & Documentation Team | To Do | 2024-06-01 | 2024-06-30