## Worksheet
Freelancer Project Template
Strategy Planning • Project Template • Version 1.0
Phase | Task Description | Owner | Start Date | End Date | Status
Phase 1: Strategy Planning | Define project vision and goals | Project Lead | 2024-04-05 | 2024-04-10 | Pending
Stakeholder Alignment & Requirements Gathering
| Conduct stakeholder interviews | Project Manager | 2024-04-11 | 2024-04-15 | In Progress
Phase 2: Market & Competitive Research | Collect industry data and trends | Data Analyst | 2024-04-16 | 2024-04-19 | In Progress
Competitive Analysis and SWOT
| Perform SWOT analysis | Business Strategist | 2024-04-20 | 2024-04-25 | Pending
Phase 3: Strategic Roadmap Creation | Develop strategic initiatives and KPIs | Strategy Lead | 2024-04-26 | 2024-05-01 | Pending
Draft Strategy Document and Review
| Finalize strategic plan with client approval | Project Lead | 2024-05-02 | 2024-05-05 | Pending
Phase 4: Execution & Timeline Setup | Create detailed project timeline (Gantt) | Project Manager | 2024-05-06 | 2024-05-10 | Pending
Resource Allocation and Risk Assessment
| Identify risks and mitigation plans | Risk Manager | 2024-05-11 | 2024-05-13 | Pending
Total Duration: |  |  |  |  | 45 Days
This template is designed for freelance professionals managing strategic project planning. Customize as needed.