## Worksheet
Strategy Planning - Project Template
Large Business Style ¦ Template Type: Project Template ¦ Purpose: Strategy Planning
Phase | Objective | Key Activities | Responsible Team | Timeline (Start - End) | Status
1. Vision & Alignment | Define long-term vision and strategic goals | Conduct stakeholder workshops, SWOT analysis, market research | Executive Leadership Team | Jan 5 - Feb 15, 2024 | In Progress
| Establish strategic pillars and KPIs | Develop performance metrics, define success criteria | Strategy & Planning Office | Feb 16 - Mar 15, 2024 | Pending
| Secure executive buy-in and approval | Presentation to board, feedback integration, final sign-off | CEO & Board of Directors | Mar 16 - Mar 31, 2024 | Pending
| Communicate vision across organization | Company-wide town halls, internal communications plan | Internal Communications Team | Apr 1 - Apr 15, 2024 | Pending
2. Market Analysis & Positioning | Assess market trends and competitive landscape | Industry benchmarking, competitor mapping, customer segmentation | Market Research & Intelligence Team | Apr 16 - May 31, 2024 | Pending
| Refine target customer personas and value proposition | Persona development, messaging strategy sessions | Marketing & Product Teams | Jun 1 - Jun 30, 2024 | Pending
| Determine optimal positioning and market entry approach | Positioning workshop, scenario planning sessions | Strategy & Sales Leadership | Jul 1 - Jul 31, 2024 | Pending
3. Strategic Roadmap Development | Create multi-year strategic roadmap | Long-range planning, milestone setting, resource allocation modeling | Strategy & Planning Office | Aug 1 - Sep 15, 2024 | Pending
| Develop annual action plans per department | Departmental alignment sessions, goal cascading framework | Department Heads & Functional Leads | Sep 16 - Oct 31, 2024 | Pending
| Establish cross-functional initiatives and synergies | Identify integration opportunities, joint projects planning | Cross-Functional Project Teams | Nov 1 - Nov 30, 2024 | Pending
| Align capital investment and budgeting with strategy | Financial modeling, ROI analysis, budget requests process | Finance & Strategy Teams | Dec 1 - Dec 15, 2024 | Pending
| Finalize and approve strategic roadmap with leadership team | Roadmap review meeting, executive sign-off process | Executive Leadership Team | Dec 16 - Dec 31, 2024 | Pending
4. Implementation & Monitoring | Launch strategic initiatives with clear accountability | Initiative kickoffs, RACI matrix documentation, communication plan | All Project Leads & Managers | Jan 1 - Jan 31, 2025 | Pending
| Implement quarterly review and performance tracking system | Dashboard setup, reporting framework development, KPI monitoring | Performance Management Team | Feb 1 - Apr 30, 2025 | Pending
| Conduct quarterly strategy review and adjustment sessions | Review performance data, market changes, strategic pivots if needed | Executive Leadership Team & Strategy Office | Mar 15 - Apr 30, 2025 (Quarterly) | Pending
Key Success Indicators & Performance Metrics
Metric |  | Target Value (Year 1) | Current Status | Measurement Frequency | Owner
Revenue Growth Rate (YoY) |  | +15% | 8.4% | Quarterly | Finance Department
Customer Retention Rate |  | ≥92% | 86.7% | Monthly | Customer Success Team
Market Share (Key Segments) |  | +3% increase | +1.2% | Quarterly | Marketing & Sales Teams
Innovation Pipeline (New Products) |  | 5 new products launched | 2 in development | Bi-Annual | R&D Department
Notes:
All timelines are subject to change based on business conditions and executive review.
Status updates should be provided every two weeks via the centralized project management portal.
This template is designed for large enterprise environments with multiple stakeholders and complex interdependencies.